## Sheet1
| Task | Status | Comments
1 | The app starts by showing the splash screen (some png image) for 2 seconds. | In progress | Need to set a timer, not it stays until clicked
2 | Then it asks user to choose a directory to open in the application. | In progress | I've disabled this option for now, since IMO it makes more sense to keep the previous directory persistent across sessions. I can add this as a checkable option
3 | The app scans the directory for PNG and JPG files. | Completed
4 | Directories that contain images from 3 should be shown in TreeView (or similar) on the left panel as categories and subcategories. There is no context (mouse right click) menu for items here. | In progress
5 | Clicking on the category should show images in this category and all subcategories in the GridView (or similar) on the right. | Completed
6 | Previews for images should have resolution 128x128px for ordinary DPI and 256x256px for High DPI environments. | Completed | At the moment I've set the size to be 1/8 screen height
7 | Double-clicking an image preview opens the image with default system image viewer. Context menu contains "Open" and "Export" items. | In progress | Need to add context menu
8 | The menubar contains "File" and "About" menus. | Completed | The menu is dummy
9 | The "File" menu contains "Export Image(s)..." and "Exit". Export menu item shows a dialog to choose where to export selected images. The images should be copied from the original location "as is". | Not started
10 | "About" menu shows a popup window with a program icon, program name, arbitrary text, link to the app's Web site and OK button. | Not started
11 | There should be a Search/Filter input for filtering images that are shown in the GridView now. The filter should search the text in a case-insensitive way using image file path from the selected root directory. For example: | Not started
12 | If the image has the path "<C://images/Backgrounds/Guitars/Fender/Sonic> Blue Telecaster.png", and the "<C://images/Backgrounds>" was opened by the app and "Guitars" subcategory is selected right now, then it should be found by any of the words in the list "Fender, Sonic, Blue, Telecaster". | Not started
13 | There should be a progress popup for Exporting/Copying images, without ability to stop/pause the export. Images with the same names in destination directory are overwritten. | Not started
14 | The app should work in a read-only manner with original images. | Completed
15 | There should be a drag control for changing width of TreeView panel. | Not started